## Week 11
CAPSTONE PROJECT 2 – WEEKLY PROGRESS REPORT WORKSHEET
AQUAPIN • WEEK 11
A. Project Information
Project Title: Aquapin: A Geotagging and Geospatial Mapping System for Aquaculture Management
Group No.: 22
Week: 11
Reporting Period: September 1–7, 2026
Adviser: Dr. Verdict L. Gonzales, PhD, DIT
Date Submitted: To be filled upon submission
Report basis: Week10.docx and the supplied Gantt chart. Task statuses follow the requested weekly progression: the previous week's ongoing tasks become completed, and its upcoming tasks become ongoing. Outputs below describe those carried-forward activities; supporting files were not supplied.
B. Team Members
1. Ian Dave Punayo
2. Angel Mae Ablog
3. Giovanni Paolo Molina
C. Weekly Summary
The team completed the activities carried over from Week 10: the initial Chapter V draft, admin dashboard testing sessions, end-to-end sync stress testing, and mobile APK multi-device testing. Work continued on preparing empirical data for Chapter V, closing the testing and validation phase, and starting the documentation groundwork for Objectives 1 and 2. Further development of these objective sections is scheduled for Week 12.
D. Completed Tasks
Task |  | Member Responsible |  | Status | Evidence / Output
Chapter V – Results and Discussion (Initial Draft) |  | Project Team |  | Done | Initial test results, data tables, and system screenshots compiled into the initial draft.
Admin Dashboard (Testing) |  | Project Team |  | Done | Dashboard testing sessions completed.
End-to-End Sync Stress Testing |  | Project Team |  | Done | Offline synchronization testing under weak network conditions completed.
Mobile APK Multi-Device Testing |  | Project Team |  | Done | APK testing on different physical Android phones completed.
E. Ongoing Tasks
Task |  | Current Status |  | Expected Completion
Continue Chapter V – Results and Discussion |  | Preparing empirical data for Objective 1 for use in Week 12. |  | Week 12
Finish Testing & Validation (Section F) |  | Consolidating testing results and finalizing the bug tracking log. |  | Week 11 target; carried forward to Week 12 under the requested progression
Start Documentation for Objectives 1 & 2 |  | Preparing the initial documentation structure and supporting material for both objective sections. |  | Initial preparation in Week 11; section development from Week 12
F. Upcoming Tasks
1. Continue the Objective 1 section of Chapter V using the prepared empirical data.
2. Continue the Objective 2 section of Chapter V by organizing its results and discussion.
3. Consolidate the Chapter V draft, including test results, data tables, and system screenshots.
G. Issues and Concerns
Previously Reported Issue (Week 10): Duplicate entries during offline sync queue retries.
Recorded Solution: Added unique transaction IDs (UUIDs) to prevent duplicate records.
Previously Reported Issue (Week 10): Map lag when loading complex pond boundary polygons on older phones.
Recorded Solution: Optimized map coordinate data and enabled polygon caching.
No additional issues or new corrective actions were supplied for Week 11.
H. Insights and Adjustments
Insight: The Week 10 report highlighted the value of physical-device testing for observing GPS and battery performance. Its test records provide supporting material for the results and discussion.
Lesson Learned: As noted in Week 10, preparing Chapter V alongside testing helps organize screenshots and test data while they are available.
Adjustment: Separate the completed initial Chapter V draft from continuing objective-specific documentation. Final validation closure remains ongoing under the requested task progression, although Week 10 listed September 1 as its target.
I. Individual Member Contribution Worksheet
Week 11 individual assignments, deliverables, and contribution percentages are to be confirmed by the team. Week 10 percentages are not treated as verified contributions for this reporting period.
Member Name | Tasks Accomplished |  | Deliverables / Evidence |  |  |  | % Contribution
Ian Dave Punayo | To be confirmed |  | To be confirmed |  |  |  | To be confirmed
Angel Mae Ablog | To be confirmed |  | To be confirmed |  |  |  | To be confirmed
Giovanni Paolo Molina | To be confirmed |  | To be confirmed |  |  |  | To be confirmed
J. Contribution Declaration
We hereby certify that the contributions listed above accurately represent the work performed during this reporting period.
Complete the contribution worksheet before signing.
Member Name |  | Signature |  |  |  | Date
Ian Dave Punayo |  | __________________________
Angel Mae Ablog |  | __________________________
Giovanni Paolo Molina |  | __________________________
Attested by: Ian Dave Punayo
Signature: __________________________
Date: __________________________
Video Link:

## Week 12
CAPSTONE PROJECT 2 – WEEKLY PROGRESS REPORT WORKSHEET
AQUAPIN • WEEK 12
A. Project Information
Project Title: Aquapin: A Geotagging and Geospatial Mapping System for Aquaculture Management
Group No.: 22
Week: 12
Reporting Period: September 8–14, 2026
Adviser: Dr. Verdict L. Gonzales, PhD, DIT
Date Submitted: To be filled upon submission
Report basis: Week10.docx and the supplied Gantt chart. Task statuses follow the requested weekly progression: the previous week's ongoing tasks become completed, and its upcoming tasks become ongoing. Outputs below describe those carried-forward activities; supporting files were not supplied.
B. Team Members
1. Ian Dave Punayo
2. Angel Mae Ablog
3. Giovanni Paolo Molina
C. Weekly Summary
The team completed the activities carried over from Week 11: preparation of empirical data for Objective 1, final testing and validation closure, and the initial documentation groundwork for Objectives 1 and 2. Ongoing work now focuses on developing both objective sections and consolidating the Chapter V draft. Completion of the preparatory work does not mean that the full objective sections are finished; their writing continues according to the Gantt chart.
D. Completed Tasks
Task |  | Member Responsible |  | Status | Evidence / Output
Continue Chapter V – Results and Discussion (Empirical Data Preparation) |  | Project Team |  | Done | Empirical data prepared for use in the Objective 1 section.
Finish Testing & Validation (Section F) |  | Project Team |  | Done | Testing results consolidated and the bug tracking log finalized.
Start Documentation for Objectives 1 & 2 (Initial Preparation) |  | Project Team |  | Done | Initial documentation structure and supporting material prepared for both objective sections.
E. Ongoing Tasks
Task |  | Current Status |  | Expected Completion
Continue Objective 1 Documentation |  | Developing the results and discussion using the prepared empirical data. |  | Week 14, per Gantt chart
Continue Objective 2 Documentation |  | Organizing and developing the results and discussion for Objective 2. |  | Week 15, per Gantt chart
Consolidate Chapter V – Results and Discussion |  | Bringing together the current draft, test results, data tables, and system screenshots. |  | Week 12 for the general Chapter V activity; objective sections continue through Weeks 14–15
F. Upcoming Tasks
1. Week 13: Begin the Objective 3 section of Chapter V while continuing the Objective 1 and Objective 2 sections.
2. Week 14: Begin the Objective 4 section of Chapter V.
3. Weeks 14–15: Work on Chapter VI – Summary, Conclusion, and Recommendation; Bibliography (APA 7th Edition) and Appendices; final manuscript proofreading, formatting, and binding; and Final Presentation (Final Defense).
G. Issues and Concerns
Previously Reported Issue (Week 10): Duplicate entries during offline sync queue retries.
Recorded Solution: Added unique transaction IDs (UUIDs) to prevent duplicate records.
Previously Reported Issue (Week 10): Map lag when loading complex pond boundary polygons on older phones.
Recorded Solution: Optimized map coordinate data and enabled polygon caching.
No additional issues or new corrective actions were supplied for Week 12.
H. Insights and Adjustments
Insight: The transition from validation to documentation brings the system test results, screenshots, and empirical data into the Chapter V discussion.
Lesson Learned: Treating data preparation, initial drafting, and continued section writing as separate stages makes weekly progress clearer.
Adjustment: Continue Objective 1 through Week 14 and Objective 2 through Week 15, as marked in the Gantt chart. Begin Objective 3 in Week 13.
I. Individual Member Contribution Worksheet
Week 12 individual assignments, deliverables, and contribution percentages are to be confirmed by the team. Week 10 percentages are not treated as verified contributions for this reporting period.
Member Name | Tasks Accomplished |  | Deliverables / Evidence |  |  |  | % Contribution
Ian Dave Punayo | To be confirmed |  | To be confirmed |  |  |  | To be confirmed
Angel Mae Ablog | To be confirmed |  | To be confirmed |  |  |  | To be confirmed
Giovanni Paolo Molina | To be confirmed |  | To be confirmed |  |  |  | To be confirmed
J. Contribution Declaration
We hereby certify that the contributions listed above accurately represent the work performed during this reporting period.
Complete the contribution worksheet before signing.
Member Name |  | Signature |  |  |  | Date
Ian Dave Punayo |  | __________________________
Angel Mae Ablog |  | __________________________
Giovanni Paolo Molina |  | __________________________
Attested by: Ian Dave Punayo
Signature: __________________________
Date: __________________________
Video Link: