## Sheet1
CAGAYAN STATE UNIVERSITY – GONZAGA CAMPUS ¦ COLLEGE OF INFORMATION AND COMPUTING SCIENCES ¦ BSIT PROGRAM
AQUAPIN: A GEOTAGGING AND GEOSPATIAL MAPPING SYSTEM FOR AQUACULTURE MANAGEMENT
Researchers: Ian Dave Punayo • Angel Mae Ablog • Giovanni Paolo Molina
Adviser: VERDICT L. GONZALES, PhD, DIT ¦ Capstone In-charge: VERDICT L. GONZALES, PhD, DIT
ACTIVITIES / WORK PLAN |  | JUNE 2026 |  | JULY 2026 |  |  |  | AUGUST 2026 |  |  |  | SEPTEMBER 2026
ID | TASK / SUB-ACTIVITY | W1 Jun 23 | W2 Jun 30 | W3 Jul 7 | W4 Jul 14 | W5 Jul 21 | W6 Jul 28 | W7 Aug 4 | W8 Aug 11 | W9 Aug 18 | W10 Aug 25 | W11 Sep 1 | W12 Sep 8 | W13 Sep 15 | W14 Sep 22 | W15 Sep 29
A. WEB ADMIN CONSOLE CORE SETUP
9 | Enhance the existing web admin interface and standardize the layout and navigation
10 | Refine the admin login, password-recovery interface, and form validation
11 | Improve the admin dashboard, summary cards, and operational overview
12 | Enhance the pond-monitoring and interactive-map interface
B. ADMIN CONSOLE DEEP CONSTRUCTION
13 | Refine the user and field-staff management features
14 | Integrate mobile operational records into the admin data views
15 | Complete responsive design and final user-interface refinements
C. BACKEND SERVICES & AI REPORTING
17 | Automated data verification, anomaly detection, and sync-error alerts
F. TESTING & SYSTEM VALIDATION
18 | Conduct adviser testing and incorporate the collected feedback
19 | Complete end-to-end testing, bug fixing, and performance optimization
20 | Deploy the production build and perform final launch verification
G. SYSTEM DOCUMENTATION
21 | Chapter I – Introduction
22 | Chapter II – Thematic Review of Related Literature
23 | Chapter III – Technical Background
24 | Chapter IV – Research Methodology (DFDs, ERD, HIPO, flowchart)
25 | Chapter V – Results and Discussion
26 | Chapter VI – Summary, Conclusion, and Recommendation
27 | Bibliography (APA 7th Edition) and Appendices
28 | Final manuscript proofreading, formatting, and binding
29 | Final Presentation (Final Defense)
GANTT USE: Shade the weekly cells corresponding to each activity’s planned or completed work period.
PREPARED BY (GROUP LEADER) |  |  |  |  | CHECKED BY (PROJECT ADVISER) | [5 empty] | NOTED BY (CAPSTONE IN-CHARGE)
Ian Dave Punayo |  |  |  |  | VERDICT L. GONZALES, PhD, DIT | [5 empty] | VERDICT L. GONZALES, PhD, DIT
Signature / Date: ________________________ |  |  |  |  | Signature / Date: ________________________ | [5 empty] | Signature / Date: ________________________