## Sheet1
CAGAYAN STATE UNIVERSITY – GONZAGA CAMPUS ¦ College of Information and Computing Sciences ¦ BSIT Program
AQUAPIN: An Aquaculture Management System with Offline-First Mobile App and Next.js Web Admin Console
GANTT CHART OF ACTIVITIES ● A.Y. 2025–2026 ● July 1 – October 19, 2026 ● FINAL DEFENSE: OCTOBER 19, 2026
Researchers: Ian Dave Punayo ● Angel Mae Ablog ● Giovanni Paolo Molina ● Renzo Recca Balboa
Adviser: ___________________________ Capstone In-charge: VERDICT L. GONZALES, PhD, DIT
★ UPDATED — Includes: Next.js Admin Dashboard (for Advisor Testing) ¦ Supabase Backend & PostGIS ¦ React Native Offline-First Sync
ACTIVITIES |  | July 2026 |  |  |  | August 2026 |  |  |  | September 2026 |  |  |  |  | October 2026
ID | Task / Sub-activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
|  | Jul 06 | Jul 13 | Jul 20 | Jul 27 | Aug 03 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 07 | Sep 14 | Sep 21 | Sep 28 | Oct 05 | Oct 12 | Oct 19
[15 empty] | ⚠DEADLINE |  | 🎓DEFENSE
A. DATABASE SCHEMA & BACKEND INITIALIZATION
1 | Supabase database schema initialization & public profiles setup | bar: July 2026 W1 Jul 06 to July 2026 W2 Jul 13
2 | Geospatial database setup with PostGIS support for pond boundaries | bar: July 2026 W2 Jul 13
3 | Admin-scoped RPC and settings audit trails database structure | bar: July 2026 W2 Jul 13
B. MOBILE APP DEVELOPMENT
4 | Mobile app navigation & Supabase client auth flow integration | bar: July 2026 W3 Jul 20 to July 2026 W4 Jul 27
5 | Local WatermelonDB/AsyncStorage offline sync queue engine | bar: July 2026 W4 Jul 27 to August 2026 W5 Aug 03
6 | Pond boundary capture map screen & GPS locator utility | bar: August 2026 W5 Aug 03
7 | Data entry logs: stocking, mortality, and harvests tracking pages | bar: August 2026 W5 Aug 03 to August 2026 W6 Aug 10
8 | Pond historical records review and sync queue status GUI | bar: August 2026 W6 Aug 10
C. WEB ADMIN CONSOLE CORE SETUP
9 | Next.js project setup, routing, and role-based route middleware | bar: August 2026 W7 Aug 17
10 | Admin authentication flow UI (Login, reset password screens) | bar: August 2026 W7 Aug 17 to August 2026 W8 Aug 24
11 | Operational overview dashboard cards & metrics cards layout | bar: August 2026 W8 Aug 24
12 | Field staff account promotion, user approvals, and profile repair flow | bar: August 2026 W8 Aug 24
D. ADMIN CONSOLE DEEP CONSTRUCTION (STARTING FROM ZERO)
13 | Interactive GIS Map Dashboard: Pond boundary visualizer & layer toggles | bar: September 2026 W9 Aug 31 to September 2026 W10 Sep 07
14 | Analytics Panel: Mortality trends, FCR, and harvest biomass charts | bar: September 2026 W10 Sep 07 to September 2026 W11 Sep 14
15 | Feed Inventory Management and stocking planning logs page | bar: September 2026 W11 Sep 14
16 | Admin Settings Console: System config editor with audit histories | bar: September 2026 W11 Sep 14 to September 2026 W12 Sep 21
E. BACKEND SERVICES & AI REPORTING
17 | AI-Powered Assistant: Report compiler & chat interface integration | bar: September 2026 W12 Sep 21
18 | Automated data verification, anomaly detection, and sync error alerts | bar: September 2026 W12 Sep 21 to September 2026 W13 Sep 28
F. TESTING & SYSTEM VALIDATION
19 | Admin Dashboard (for Advisor Testing) | bar: September 2026 W13 Sep 28 to October 2026 W14 Oct 05
20 | End-to-end sync testing, bug reporting, and unit test suites | bar: October 2026 W14 Oct 05 to October 2026 W15 Oct 12
21 | Expo EAS native builds compilation & Next.js production hosting deployment | bar: October 2026 W15 Oct 12 to October 2026 W16 Oct 19
G. SYSTEM DOCUMENTATION
22 | Chapter I – Introduction (incl. system scope & objectives) | bar: July 2026 W1 Jul 06 to July 2026 W4 Jul 27
23 | Chapter II – Thematic Review of Related Literature | bar: July 2026 W2 Jul 13 to August 2026 W5 Aug 03
24 | Chapter III – Technical Background (Supabase, React Native, Next.js) | bar: July 2026 W4 Jul 27 to August 2026 W6 Aug 10
25 | Chapter IV – Research Methodology (DFDs, ERD, HIPO, Flowchart) | bar: August 2026 W6 Aug 10 to September 2026 W9 Aug 31
26 | Chapter V – Results & Discussion | bar: September 2026 W13 Sep 28 to October 2026 W15 Oct 12
27 | Chapter VI – Summary, Conclusion & Recommendation | bar: October 2026 W15 Oct 12 to October 2026 W16 Oct 19
28 | Bibliography (APA 7th Edition) & Appendices | bar: October 2026 W15 Oct 12 to October 2026 W16 Oct 19
29 | Final Manuscript Proofreading, Formatting & Binding | bar: October 2026 W16 Oct 19
⚠ ALL SOFTWARE DEVELOPMENT & INTEGRATION TASKS MUST BE COMPLETED BY OCT 05 (W14) — 2 WEEKS BEFORE FINAL DEFENSE ON OCTOBER 19, 2026
LEGEND: | A. Requirements & DB Setup | July 2026 W1 Jul 06: B. Mobile Development; July 2026 W2 Jul 13: C. Web Console Core; July 2026 W3 Jul 20: D. Admin Construction; July 2026 W4 Jul 27: E. Backend & AI Services; August 2026 W5 Aug 03: F. Testing & Validation; August 2026 W6 Aug 10: G. Documentation Chapters; August 2026 W7 Aug 17: ⚠ Oct 05 Deadline / 🎓 Oct 19 Defense
Prepared by (Group Leader): ___________________________ Date: ___________ | Checked by (Adviser): ___________________________ Date: ___________ | July 2026 W1 Jul 06: Noted by (Capstone In-charge): ___________________________ Date: ___________
Ian Dave Punayo | Project Adviser | July 2026 W1 Jul 06: VERDICT L. GONZALES, PhD, DIT
Aquapin ● BSIT Program ● Cagayan State University – Gonzaga Campus ● A.Y. 2025–2026 ● Long Bond Paper / Transparent Clearbook