## Gantt Chart
CAGAYAN STATE UNIVERSITY – GONZAGA CAMPUS ¦ College of Information and Computing Sciences ¦ BSIT Program
NEXUSHOME: A Smart Home Automation System with Intelligent Temperature Monitoring
GANTT CHART OF ACTIVITIES ● A.Y. 2025–2026 ● June 9 – October 2, 2025 ● FINAL DEFENSE: OCTOBER 2, 2025
Researchers: SANTIAGO ● MARIMON ● DE LA CRUZ ● FLORES Adviser: ___________________________ Capstone In-charge: VERDICT L. GONZALES, PhD, DIT
★ UPDATED — Includes: Solar-Assisted Battery Backup Subsystem ¦ 4-Channel Relay: Light, Electric Fan, Motorized Curtain, Night Lamp ¦ VC-02 Voice Range: 5–8 meters
ACTIVITIES |  |  |  | June 2025 |  |  |  | July 2025 |  |  |  | August 2025 |  |  |  | September 2025
Task / Sub-activity |  |  |  | W1 Jun 09 | W2 Jun 16 | W3 Jun 23 | W4 Jun 30 | W5 Jul 07 | W6 Jul 14 | W7 Jul 21 | W8 Jul 28 | W9 Aug 04 | W10 Aug 11 | W11 Aug 18 | W12 Aug 25 | W13 Sep 01 | W14 Sep 08 ⚠DEADLINE | W15 Sep 15 | W16 Sep 22 | W17 Sep 29 🎓DEFENSE
A. REQUIREMENTS PLANNING
1 | 1. Identify problems of existing home systems & literature review |  |  | ✓ | ✓
2 | 2. Conduct interviews with respondents / users |  |  | ✓ | ✓
3 | 3. Design & administer survey questionnaire |  |  |  | ✓ | ✓
4 | 4. Analyze gathered data & define system requirements |  |  |  |  | ✓ | ✓
5 | 5. Document functional & non-functional requirements | [5 empty] | ✓
B. USER DESIGN
6 | 6. Design Use-Case Diagram | [5 empty] | ✓
7 | 7. Design Data Flow Diagram (DFD – Context & Level 1) | [5 empty] | ✓ | ✓
8 | 8. Design Entity Relationship Diagram (ERD) | [6 empty] | ✓
9 | 9. Design HIPO Chart | [6 empty] | ✓
10 | 10. UI/UX Wireframes – Bluetooth Mobile App | [6 empty] | ✓ | ✓
11 | 11. Hardware Circuit Architecture Design (incl. solar backup) | [6 empty] | ✓ | ✓
12 | 12. Design review & adviser approval | [7 empty] | ✓
C. SYSTEM DEVELOPMENT (CONSTRUCTION)
13 | 13. Circuit Setup – ESP32 + DHT11 + OLED Display | [7 empty] | ✓ | ✓
14 | 14. Homepage / Main Dashboard UI (Bluetooth Mobile App) | [8 empty] | ✓ | ✓
15 | 15. Bluetooth Connection Module (ESP32 ↔ Mobile App) | [8 empty] | ✓ | ✓
16 | 16. VC-02 Offline Voice Recognition Integration | [9 empty] | ✓ | ✓
17 | 17. 4-Channel Relay – Light & Electric Fan Control | [9 empty] | ✓ | ✓
18 | 18. Relay Ch. 3 – Motorized Curtain Control ★ NEW | [10 empty] | ✓ | ✓
19 | 19. Relay Ch. 4 – Night Lamp Control ★ NEW | [10 empty] | ✓ | ✓
20 | 20. OLED Display – Real-time Temperature & System Status | [11 empty] | ✓
21 | 21. Automatic Temperature Mode Logic (DHT11-triggered fan) | [11 empty] | ✓ | ✓
22 | 22. Manual Control Mode via Mobile App | [11 empty] | ✓
23 | 23. Activity Logs & Real-time Status Feedback on App | [12 empty] | ✓
C2. SOLAR-ASSISTED BACKUP POWER SUBSYSTEM ★ NEW
24 | 24. Solar Panel + Rechargeable Battery Circuit Setup ★ NEW | [9 empty] | ✓ | ✓
25 | 25. Automatic Power-Switching Mechanism (Main ↔ Battery) ★ NEW | [10 empty] | ✓ | ✓
26 | 26. Low-Power Mode Logic During Brownout / Blackout ★ NEW | [11 empty] | ✓ | ✓
27 | 27. Solar Charging Monitoring & Status Indicator ★ NEW | [12 empty] | ✓
28 | 28. Integration of Backup Subsystem with Main NexusHome System ★ NEW | [13 empty] | ✓
C3. FULL SYSTEM INTEGRATION & REFINEMENT
29 | 29. Full System Integration & Debugging (all modules) | [13 empty] | ✓
30 | 30. Iteration & Refinement based on initial testing | [14 empty] | ✓
D. TESTING & EVALUATION
31 | 31. Unit Testing (ESP32, DHT11, VC-02, Relay, OLED individually) | [14 empty] | ✓
32 | 32. Integration Testing (all modules combined) | [14 empty] | ✓
33 | 33. Solar Backup Subsystem Testing (switching, charging) ★ NEW | [14 empty] | ✓
34 | 34. System Testing (end-to-end: voice, BT, relay, solar, temp) | [15 empty] | ✓
35 | 35. User Acceptance Testing (UAT) – homeowner respondents | [15 empty] | ✓
36 | 36. ISO/IEC 25010 Quality Evaluation (survey-based) | [15 empty] | ✓
37 | 37. System deployment in controlled residential setting | [15 empty] | ✓
E. DOCUMENTATION
38 | 38. Chapter I – Introduction (incl. solar backup & 4 appliances) |  |  | ✓ | ✓ | ✓ | ✓
39 | 39. Chapter II – Thematic Review of Related Literature |  |  |  | ✓ | ✓ | ✓ | ✓
40 | 40. Chapter III – Technical Background (incl. solar hardware) ★ UPD | [5 empty] | ✓ | ✓ | ✓
41 | 41. Chapter IV – Research Methodology (DFDs, ERD, HIPO, Flowchart) | [7 empty] | ✓ | ✓ | ✓ | ✓
42 | 42. Chapter V – Results & Discussion | [14 empty] | ✓ | ✓
43 | 43. Chapter VI – Summary, Conclusion & Recommendation | [15 empty] | ✓
44 | 44. Bibliography (APA 7th Edition) & Appendices | [15 empty] | ✓
45 | 45. Final Manuscript Proofreading, Formatting & Binding | [15 empty] | ✓
⚠ ALL TASKS MUST BE COMPLETED BY SEPT 15 (W14) — 2 WEEKS BEFORE FINAL DEFENSE ON OCTOBER 2, 2025 |  |  |  | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE | ← ACTIVE |  |  | 🎓 DEFENSE
LEGEND: |  | A. Requirements Planning | B. User Design |  | C. System Development |  |  | C2. Solar Backup ★ NEW |  |  | C3. Integration |  |  | D. Testing & Evaluation |  |  | E. Documentation |  |  | ⚠ Deadline W14 / 🎓 Defense W17
Prepared by (Group Leader): ________________________________ Date: ___________ | [6 empty] | Checked by (Adviser): ________________________________ Date: ___________ | [6 empty] | Noted by (Capstone In-charge): ________________________________ Date: ___________
NexusHome ● BSIT Program ● Cagayan State University – Gonzaga Campus ● A.Y. 2025–2026 ● Long Bond Paper / Transparent Clearbook